## Sheet1
Gantt Chart for software engineering group 26C
Task | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23
Designing UML Diagrams
Submit stage 2
Finalise Class and Sequence diagrams
Develop the Application part 1
Test application
Develop the Application part 2
Final testing
Compile final version of application
Submit stage 3
Task | Start Date | Duration | End Date
Designing UML Diagrams | 29/1/2017 | 8 | 2017-05-02
Submit stage 2 | 2017-06-02 | 1 | 2017-06-02
Finalise Class and Sequence diagrams | 2017-06-02 | 2 | 2017-07-02
Develop the Application part 1 | 2017-08-02 | 5 | 2017-12-02
Test application | 2017-12-02 | 2 | 13/2/2017
Develop the Application part 2 | 13/2/2017 | 5 | 17/2/2017
Final testing | 17/2/2017 | 2 | 18/2/2017
Compile final version of application | 19/2/2017 | 1 | 19/2/2017
Submit stage 3 | 20/2/2017 | 1 | 20/2/2017
Task | Start Date | Duration | End Date
Designing UML Diagrams | 2017-01-29 | 8 | 2017-02-05
Submit stage 2 | 2017-02-06 | 1 | 2017-02-06
Finalise Class and Sequence diagrams | 2017-02-06 | 2 | 2017-02-07
Finish UML | 2017-02-07 | 8 | 2017-02-11
Designing Test Plan | 2017-02-09 | 3 | 2017-02-11
Develop Application | 2017-02-11 | 9 | 2017-02-19
Test application | 2017-02-12 | 2 | 2017-02-13
Final testing | 2017-02-17 | 2 | 2017-02-18
Compile final version of application | 2017-02-19 | 1 | 2017-02-19
Code Review | 2017-02-19 | 2 | 2017-02-20
Submit stage 3 | 2017-02-20 | 1 | 2017-02-20